# Risk Register: Automated Non-PO Invoice Coding

Workshop Preparation Document | Springtime Technologies | September 2026

# 1. Purpose

This document identifies the key risks facing the automated non-PO invoice coding project, assesses their likelihood and impact, and defines mitigation strategies and owners. It is intended for discussion during the Vienna workshop and will be maintained as a living document throughout the project.

# 2. Risk Assessment Matrix

Likelihood: Low / Medium / High

Impact: Low / Medium / High

Risk Score = Likelihood x Impact. High-High risks require immediate mitigation planning before project commencement.

| ID | Risk | Category | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Historical data contains systematic errors inherited from deterministic skills | Data | Medium | High | Audit seed data before indexing; sample and validate against client ERP records; tag seed data distinctly from learned outcomes | Data Scientist |
| R-02 | Current system does not capture human corrections; learning loop starts from zero | Data | High | Medium | Instrument correction capture as first priority; if impossible, rely on shadow mode outcomes and conversational input only | Platform Engineer |
| R-03 | Corpus pollution from bad corrections during a policy change or vendor acquisition | Data | Medium | High | Staging area for suspicious corrections; outlier detection; manager review queue before indexing; reversibility | Data Scientist |
| R-04 | pgvector retrieval performance degrades at enterprise scale (millions of vectors) | Technical | Medium | Medium | HNSW index tuning; tenant partitioning; hybrid retrieval (BM25 + dense); caching hot vendors; horizontal scaling | Platform Engineer |
| R-05 | Tenant isolation failure: cross-client data leakage in retrieval | Technical | Low | High | Strict tenant filter on every query; separate collections or row-level security; audit cross-tenant queries quarterly | Platform Engineer |
| R-06 | LLM API latency or cost exceeds operational budget | Technical | Medium | Medium | Conservative exception threshold; LLM only for ambiguous cases; fallback to deterministic engine; caching parsed conversational rules | AI Engineer |
| R-07 | Shadow mode accuracy plateaus below 85%; live pilot cannot proceed | Operational | Medium | High | Extended shadow period; additional feature engineering (amount bands, entity-specific weighting); client-specific tuning; pivot to hybrid approach if needed | Data Scientist |
| R-08 | Client refuses migration despite accuracy proofs | Operational | Medium | Medium | Voluntary migration only; keep deterministic engine available; client-specific ROI case studies; phased A-B testing | Client Success Manager |
| R-09 | Deterministic engine has no API; fallback path is theoretical | Operational | High | High | Map engine structure during Day 2 code dive; build adapter layer if needed; ensure fallback is tested before live pilot | AI Engineer |
| R-10 | Audit trail gap: one component fails to log to central trace | Compliance | Low | High | Centralised logging middleware; trace ID propagated through every service; automated trace completeness checks; append-only storage | Compliance Auditor |
| R-11 | Retention policy mismatch: client requires 10 years, system designed for 7 | Compliance | Medium | Medium | Confirm retention requirements per jurisdiction during discovery; design storage for longest required retention; tiered storage for cost control | Compliance Auditor |
| R-12 | AP clerk distrust: confirms without reading or corrects good predictions | Human | Medium | Medium | Clear evidence display; clerk feedback on system learning; gamification of correction quality; training on how to use evidence | AP Manager |
| R-13 | Conversational rule abuse: overly broad or contradictory rules | Human | Medium | Medium | Rule validation before application; conflict detection dashboard; admin review for broad rules; user can only retract own rules | AP Manager |
| R-14 | Drift detection false positives: legitimate policy changes flagged as errors | Data | Medium | Medium | Manager review before auto-threshold adjustment; manual accept/reject of drift events; gradual threshold restoration | Data Scientist |
| R-15 | Professional services team resistance: perceived threat to job security | Human | Medium | Medium | Clear communication that role shifts to client success and exception handling; involve PS team in shadow mode validation; measure and celebrate hours saved | Project Lead |

# 3. High-Priority Risks Requiring Immediate Attention

The following risks score High-High or High-Medium and must be addressed before or during the workshop.

R-02: Correction capture gap. If the existing system does not log overrides, the learning loop is severely handicapped. This must be confirmed during the Day 2 code dive.

R-09: Deterministic engine fallback. If the old engine cannot be called as a service, the safety net does not exist. This is a project-blocking discovery.

R-05: Tenant isolation. A single cross-tenant leak is a compliance breach. The architecture must be validated against this before any client data enters the vector store.

# 4. Risk Monitoring

This register will be reviewed weekly during active development and monthly during operations (perhaps to be hosted in Jira). New risks will be added, mitigated risks will be downgraded, and closed risks will be archived (again, in Jira via API for full transparency)